# Huawei Cloud Stack DevOps Requirements & DB Infrastructure Blueprint

ABSA-like enterprise banking constraints | Draft for review with Pragasen

Date: 9 February 2026  |  Version: 0.2  |  Author: Verash Adams

CONFIDENTIAL – Internal working document. Do not distribute outside the project team without approval.

# Document control

| Version | Date | Author | Notes / Change summary |
| --- | --- | --- | --- |
| 0.1 | 9 February 2026 | Verash Adams | Initial draft: DevOps requirements, Terraform/pipeline identity, DB baseline and risks. |
| 0.2 | <dd mmm yyyy> | Verash Adams | Update after Phase 0 clarifications and Huawei workshops. |
| 1.0 | <dd mmm yyyy> | Verash Adams | Baseline approved for MVP (single VM) and RDS environment blueprint. |

# Key decisions required (Phase 0)

To progress quickly without a full delivery re-org, we need answers to five items. These determine the authentication pattern, networking prerequisites, and the pipeline/approval model.

| Question | Why it matters | Answer options / implication |
| --- | --- | --- |
| 1) Azure DevOps type: Azure DevOps Services (cloud) or Azure DevOps Server (on-prem)? | Determines whether the agent VM must reach dev.azure.com over the internet, or only an internal ADO Server endpoint. | Services: outbound HTTPS required from Huawei Cloud Stack to Microsoft endpoints. Server: internal connectivity only. |
| 2) Terraform provider choice supported in Huawei Cloud Stack: huaweicloud or hcs/hcso? | Provider choice drives supported resources, authentication options, and long-term maintainability. | Prefer an actively maintained provider supported for the target HCS version. Some HCS-specific providers have known maintenance risk. |
| 3) Can the tenant use agencies and temporary credentials, or must we start with long-lived AK/SK? | This decides the security posture for pipelines (short-lived tokens vs static keys). | Preferred: agency + temporary AK/SK + security token. Fallback: dedicated service user with AK/SK + rotation plan. |
| 4) Team size (3–5 or 6–10) and is there a second production approver besides you? | Drives branching strategy, required segregation of duties, and pipeline approval gates. | If 2nd approver required: enforce environment approvals + protected branches; else: peer-review + audit evidence. |
| 5) Any ABSA RDS baseline references available from stakeholders? | Prevents re-inventing baseline controls and aligns quickly to stakeholder expectations (backup, HA, logging, encryption, etc.). | If available: implement as-is. If not: use the baseline proposed in this document and validate in a workshop. |

# Executive summary

This document captures a practical DevOps blueprint for deploying infrastructure and database services into a Huawei Cloud Stack (HCS) environment under typical enterprise banking constraints. It is written to create immediate delivery order (repeatability, traceability, least privilege and audit) without requiring a full organisational re-structure up front.

The immediate MVP is a single VM deployed via Terraform from an Azure DevOps pipeline running on a self-hosted agent VM inside HCS. That MVP proves end-to-end authentication, network reachability, state management, approvals and audit evidence. The larger goal is an ABSA-mimic managed database (RDS-style) environment baseline that can be re-used by multiple application teams.

## What you will get if we follow this design

A clear pipeline identity model (non-human) for Terraform runs, with an upgrade path from static AK/SK to temporary credentials.

A repeatable Terraform workflow (plan/apply separation, remote state, code review, approvals, and drift control).

A standard baseline for DB infrastructure (network isolation, encryption, backups, monitoring, and access controls).

A simple but effective work-tracking approach so developers always know what is now/next and stakeholders can see progress.

## What is intentionally out of scope for this draft

Full landing zone build-out for all banking domains (this draft assumes core network and tenancy exists or is being delivered in parallel).

Teams integration for work items and notifications (later phase).

Enterprise-wide process re-org; instead we define minimum viable governance gates inside Azure DevOps.

# Proposal for Pragasen sign-off

This section is prepared for Pragasen’s review and sign-off. It summarises the delivery intent, phased outcomes, governance controls, and the key concerns/decisions required to de-risk delivery under ABSA-style enterprise banking constraints.

| Item | Value |
| --- | --- |
| Project | CloudForgeX delivery platform plus ABSA-mimic RDS migration sandbox on Huawei Cloud Stack |
| Owner | Verash Adams |
| Approver | Pragasen |
| Implementation team | RedMps infrastructure engineers |
| Delivery model | Kanban continuous flow, automation first |
| Execution model | Azure DevOps Pipelines using a self-hosted agent VM inside Huawei Cloud Stack |

## Meeting concerns and required decisions (talk track)

Before scaling beyond the confidence MVP, the following concerns should be acknowledged and decisioned. They are also reflected in the Risk Register (Section 7) and the Phase 0 decision list.

Terraform identity and authentication model is not yet confirmed (agency + temporary credentials vs long-lived AK/SK).

Self-hosted Azure DevOps agent VM becomes part of the delivery chain and must be designed for resilience, hardening, monitoring, and patching.

Environment boundaries and approval model must be explicit (nonprod vs prod, plan/apply gating, evidence pack requirements, and separation of identities).

ABSA-mimic RDS baseline values are not yet confirmed (HA, backups, encryption/KMS, monitoring, maintenance windows, and network patterns).

Work tracking and reporting must be lightweight but consistent to create order in a messy delivery landscape (one backlog, weekly updates, decision log).

Decisions required this week (minimum set to unblock execution):

Azure DevOps type: Azure DevOps Services (cloud) or Azure DevOps Server (on-prem).

Terraform provider supported in Huawei Cloud Stack: hcso provider or huaweicloud provider.

Credential approach: can the tenant use agencies and temporary credentials, or must we start with AK/SK long-lived keys.

Team size (3–5 or 6–10) and whether there is a second production approver besides Verash Adams.

Any ABSA RDS baseline references available from stakeholders.

## 1) Executive summary

The single VM deployment is a confidence MVP to prove the delivery platform end to end (repo, pipelines, approvals, evidence pack, destroy). Once the team trusts the platform, we roll into an ABSA-mimic RDS environment blueprint to de-risk the full database migration programme. This will mirror ABSA delivery controls: gated production changes, enforced reviews, evidence packs, and strict separation of identities.

## 2) Outcomes

Phase 1 outcome: Team can deploy and destroy a test VM reliably from Azure DevOps, with evidence and approvals.

Phase 2 outcome: Terraform delivery factory is in place (modules, state, pipelines, guardrails) and usable across clients.

Phase 3 outcome: ABSA-mimic RDS baseline environment (nonprod and prod patterns) is ready, plus migration workflow templates to run waves safely.

## 3) Timelines (including 30% buffer)

Phase 1: Confidence MVP (3 to 7 working days)

Self-hosted agent VM operational

PR validation pipeline working

Nonprod deploy pipeline working

Single VM deploy and destroy working

Evidence pack generated per run

Phase 2: Platform foundations complete (about 3 weeks)

Multi-client Boards model live

Repo standards and required reviewers enforced

Remote state and serialization controls in place

Nonprod and prod pipelines separated with approvals

RBAC pipeline prepared (if approved)

Dashboards and weekly reporting baseline

Phase 3: ABSA-mimic RDS environment and migration enablement (about 5 to 16 weeks)

RDS module baseline (HA, backups, encryption, monitoring)

Environment patterns per tier

Migration wave tracker, validation gates, rollback approach

Drift detection, evidence automation expanded

Later phase: Teams integration for migration communications

## 4) Scope

### In scope now

Azure DevOps Boards setup (one project, multi-client areas, Kanban)

Self-hosted agent VM inside Huawei Cloud Stack

Terraform repo layout, module patterns, quality gates

Pipelines: PR validation, nonprod deploy, prod deploy (gated), RBAC pipeline (optional but recommended)

Remote state strategy, evidence pack automation

MVP single VM deployment (confidence test)

### In scope next

ABSA-mimic RDS baseline environment build (HA, backups, monitoring, security)

Migration wave templates and execution model

### Out of scope for now

Full clean-up of messy subscriptions and legacy structures (guardrails first, cleanup iteratively)

Actual production database migrations (enabled later once mimic is signed off)

## 5) Governance and enforceable controls

No direct pushes to main.

PR required with build validation checks.

Mandatory reviewers for sensitive paths: pipelines, RBAC, prod-affecting modules.

Production deploy requires Azure DevOps Environment approvals.

Separation of identities for nonprod, prod, and RBAC changes.

Junior engineers cannot implement “system behaviour changes” without review (defined as changes to pipelines, RBAC, network, Terraform modules that affect prod, or any change that alters platform behaviour).

## 6) Dependencies and information required

Verash Adams will engage with Jenile (Huawei) to confirm ABSA-aligned baseline values. That engagement will complete the “variables sheet” and decision log for: network, security, RDS standards, auth model, and approvals. Workshops are recommended to validate the baseline and guardrails with stakeholders before scaling.

Inputs required from ABSA/Huawei teams:

Approval to provision and operate the self-hosted agent VM in Huawei Cloud Stack.

Terraform automation identity model (nonprod and prod, plus RBAC if permitted).

Confirmation of Terraform provider supported in HCS.

Confirmation whether agencies and temporary credentials are supported or we start with AK/SK.

RDS gold standard baseline values (engines, versions, HA, backups, encryption, monitoring, maintenance windows).

Production approval chain and evidence requirements.

## 7) Sign-off requests

Please sign off on:

Self-hosted Azure DevOps agent VM inside Huawei Cloud Stack.

Pipeline model and separation (PR validation, nonprod deploy, prod gated deploy, RBAC pipeline).

Guardrails: required reviewers, environment approvals, controlled prod changes.

Phase approach: confidence MVP first, then ABSA-mimic RDS build.

# 1. Context and constraints

Provided context (as of 9 February 2026):

Cloud target: Huawei Cloud Stack (bank-style environment).

Pipeline execution must run on a self-hosted Azure DevOps agent VM inside Huawei Cloud Stack; Microsoft-hosted agents are not allowed.

Starting from ground zero for Terraform authentication and pipeline identity.

Delivery landscape is messy; design must create order without requiring a full re-org up front.

Weekly work types: Terraform/infra deployment, pipeline changes, architecture and service design, break-and-fix, meeting notes and actions.

Internal collaboration tool: Microsoft Teams (Slack out of scope; Teams integration later).

MVP: a single VM deployment to build trust; long-term: ABSA-mimic RDS environment baseline.

# 2. Banking-style constraints we must assume until proven otherwise

Unless stakeholders confirm exceptions, assume the following constraints apply:

Strict separation between non-production and production (network, IAM, and data).

Least privilege access controls and non-human pipeline identities; avoid personal accounts for automation.

Change control for production (approvals, evidence, and rollback plans).

Auditability: immutable logs, traceability from ticket -> code change -> pipeline run -> deployed change.

Restricted egress to the internet; allow-listing and proxy usage may be required.

Encryption in transit and at rest for all sensitive workloads; KMS-managed keys preferred.

Backup, retention, and disaster recovery requirements for databases.

# 3. Target architecture overview

At a high level, Terraform runs inside Azure DevOps pipelines, but the execution environment is an HCS-hosted agent VM. That agent authenticates to Huawei Cloud Stack APIs using a dedicated pipeline identity. Terraform uses a remote state backend (typically OBS using an S3-compatible backend), so multiple engineers and pipelines have consistent state.

## 3.1 Logical flow (pipeline to cloud)

Developer creates/updates Terraform code in repo (PR/merge request).

Pipeline runs Terraform fmt/validate, then Terraform plan using non-prod credentials; plan is published as an artefact.

A manual approval gate (or a second approver) triggers Terraform apply against the target environment.

Terraform uses remote state (OBS bucket) and logs outputs to pipeline for audit evidence.

Monitoring/logging captures infra and DB service events (cloud audit + service logs).

## 3.2 Minimal reference component list

| Component | Purpose | Notes |
| --- | --- | --- |
| Azure DevOps (Services or Server) | Source control, pipelines, work tracking, approvals | Key decision: cloud vs on-prem. |
| Self-hosted agent VM(s) in HCS | Runs pipeline jobs where Terraform executes | Hardened image, patched, access-controlled. |
| Terraform + provider | Provision HCS resources declaratively | Provider support must match HCS version. |
| Pipeline identity (IAM user or agency) | AuthN/AuthZ for Terraform to call HCS APIs | Prefer temporary credentials via agency. |
| Remote state backend (OBS) | Shared Terraform state and state history | Use S3-compatible backend endpoints; enable versioning. |
| Network (VPC/Subnets/SG/NACL) | Isolates workloads and controls access to DBs | Private subnets for DBs. |
| Managed DB service (RDS-style) or DB on VMs | Database hosting and operations baseline | Prefer managed where available. |

## 3.3 Roles and responsibilities (RACI – draft)

This is a suggested split to reduce confusion in a messy landscape:

| Work area | Responsible | Accountable | Consulted / Informed |
| --- | --- | --- | --- |
| Azure DevOps pipelines & templates | RedMps infrastructure engineers | Platform lead – Verash Adams | Security, App leads |
| Agent VM build & patching | RedMps infrastructure engineers | Platform lead – Verash Adams | Security, Huawei |
| HCS IAM policies/roles/agencies | Security/IAM + Platform | Security/IAM owner | Huawei, Platform lead – Verash Adams |
| Network (subnets, firewalls, DNS, proxy) | Network team | Network owner | Platform, Huawei |
| Terraform module library | RedMps infrastructure engineers | Platform lead – Verash Adams | App teams |
| RDS baseline (HA, backups, patch windows) | DBA + Platform | DBA owner | Security, Huawei, App teams |
| Break-glass and incident response | Ops/Run team | Ops owner | Platform, Security, DBA |

# 4. DevOps requirements (what you need to know)

This section is the core checklist. If these requirements are met, we can deliver the MVP VM and then iterate towards a standard RDS baseline.

## 4.1 Azure DevOps and pipeline design requirements

An Azure DevOps Agent Pool dedicated to HCS workloads (e.g., 'HCS-NonProd', 'HCS-Prod').

At least one self-hosted agent VM per environment (or per security zone). Avoid mixing prod/non-prod credentials on the same agent.

Agent VM must have network reachability to Azure DevOps (Services: dev.azure.com endpoints; Server: internal ADO URL) and to HCS API endpoints.

Pipelines must separate plan vs apply and implement approvals for apply into shared or production environments.

Branch protection and pull request reviews are mandatory for infrastructure-as-code (IaC).

Pipeline logs and artefacts must be retained for audit (retention aligned to policy).

## 4.2 Self-hosted agent VM baseline requirements

Minimum baseline (refine with the bank hardening standard):

OS: hardened Linux (preferred) or hardened Windows Server, aligned with enterprise patching.

Compute: start small for MVP (e.g., 2–4 vCPU, 8–16 GB RAM) and scale based on pipeline load.

Disk: OS + separate volume for build workspace if required; enable encryption at rest.

Installed tools: git, Terraform (pinned version), provider plugins, cloud CLI/SDK as needed, jq, unzip, ca-certificates.

Outbound proxy settings if internet egress is controlled (common in bank environments).

Enterprise root CA certificates installed if HTTPS inspection / internal PKI is used.

Agent runs as a service account (not a personal user).

Logging: ship agent logs to central logging or retain for a defined period.

Patching: schedule monthly patch window; treat agents as Tier-2 infrastructure.

## 4.3 Terraform workflow requirements

Recommended workflow to reduce risk and increase auditability:

Repository structure that separates reusable modules from environment stacks.

Remote state stored in OBS (S3-compatible) per environment + per stack, with versioning enabled.

State encryption enabled and bucket access restricted to pipeline identity and break-glass admins.

Plan output captured as pipeline artefact and attached to the change request (evidence).

Apply must run only from the default branch with approvals; no direct applies from feature branches.

Use input variables and tfvars per environment; avoid hard-coding endpoints and IDs.

Tagging and naming standards enforced by code (variables + policy-as-code where possible).

Drift management: scheduled plan runs against main to detect drift; define a process to reconcile.

## 4.4 Identity, credentials, and secrets requirements

The biggest early blocker is usually 'what identity does the pipeline use' and 'where do we store secrets'. Start with a safe minimum and design the upgrade path.

### 4.4.1 Credential options

| Option | How it works | Pros | Cons / risks |
| --- | --- | --- | --- |
| A) Long-lived AK/SK (service user) | Create an IAM service user for Terraform. Store AK/SK in Azure DevOps secret variables/variable group. Terraform provider uses AK/SK. | Fastest to start. Works even if agencies/STS are not enabled. | Key leakage risk. Requires rotation process. Often disallowed for production without compensating controls. |
| B) Agency + temporary AK/SK + security token (preferred) | Pipeline authenticates as a trusted user/service, assumes an agency/role, and requests temporary AK/SK + token for short TTL. | Least privilege + short-lived creds; better audit and lower blast radius. | Requires IAM agency setup and a token issuance flow; slightly more upfront work. |
| C) Break-glass manual credentials (not for steady state) | A human runs apply with elevated credentials for emergencies only. | Useful for incident recovery. | Not scalable; breaks audit separation if used routinely. |

### 4.4.2 Secrets storage and handling rules

Never store AK/SK or tokens in repo, wiki pages, or chat.

Use Azure DevOps secret variables / variable groups initially; move to an enterprise secret manager when available (later phase).

Restrict who can view/edit pipeline variables and service connections.

Mask secrets in pipeline logs; disable command echo where needed.

Rotate any long-lived keys at a fixed cadence (e.g., 60–90 days) and after any suspected exposure.

Use separate credentials per environment (non-prod, prod).

## 4.5 Network and connectivity requirements

Connectivity issues are a common reason self-hosted agents 'work in a lab but fail in a bank'. Treat this as a deliverable, not an assumption.

| Source | Destination | Port/Protocol | Purpose | Notes |
| --- | --- | --- | --- | --- |
| Agent VM | Azure DevOps (Services) dev.azure.com | 443/HTTPS | Pipeline job execution, repo access, artefact upload | If egress restricted, allow-list + proxy required. |
| Agent VM | Azure DevOps Server (on-prem) | 443/HTTPS | Pipeline job execution internal | Internal routing + TLS cert trust required. |
| Agent VM | HCS IAM endpoint | 443/HTTPS | Obtain tokens / authenticate API calls | May require enterprise CA / TLS inspection compatibility. |
| Agent VM | HCS service APIs (ECS/VPC/RDS/OBS/KMS) | 443/HTTPS | Provision and manage resources via Terraform | Confirm service endpoints per region/tenant. |
| Agent VM | Git/Repo (if separate) | 443/HTTPS or SSH | Source checkout | Prefer HTTPS with PAT/credentials; align with enterprise policy. |
| Agent VM | Package/artifact feeds | 443/HTTPS | Download Terraform, provider plugins, dependencies | If offline: mirror packages internally. |
| All nodes | NTP | 123/UDP | Time sync (critical for TLS and tokens) | Use enterprise NTP servers. |
| All nodes | DNS | 53/UDP/TCP | Name resolution | Private DNS zones for internal endpoints. |

## 4.6 Minimum required Huawei Cloud Stack services and permissions

For the MVP and DB baseline, expect to need access to the following service areas:

IAM: users/roles/agencies, policies, access keys (and ideally temporary credential APIs).

Networking: VPC, subnets, route tables, security groups, NAT/egress controls (where applicable).

Compute: VM instances (ECS), images (IMS), volumes (EVS), key pairs.

Storage: OBS bucket for Terraform state and optionally logs/backups exports.

Database: RDS service (or equivalent) including parameter groups, backup settings, and monitoring integrations.

KMS (or equivalent): key management for encryption at rest.

Least privilege approach: create separate IAM policies for (a) MVP VM provisioning and (b) RDS baseline provisioning. Avoid granting broad administrator roles to the pipeline identity; use break-glass for emergencies.

## 4.7 Terraform repo and module pattern (creates order without re-org)

Recommended repo structure (single repo to start; split later if needed):

/infra
  /modules
    /network
    /compute_vm
    /rds_baseline
  /envs
    /nonprod
      main.tf
      variables.tf
      nonprod.tfvars
    /prod
      main.tf
      variables.tf
      prod.tfvars
  /pipelines
    terraform-nonprod.yml
    terraform-prod.yml

Key idea: modules are reusable building blocks; envs are opinionated stacks that consume modules with environment-specific variables.

# 5. How to implement the infrastructure for databases (RDS-style baseline)

The goal is a reusable baseline that looks and feels like an enterprise managed database platform: secure by default, isolated, monitored, with predictable onboarding for application teams. The baseline can be implemented using HCS managed DB services (preferred) or, if unavailable, DBs on VMs with a stricter operations model.

## 5.1 Baseline building blocks

Network isolation: DBs in private subnets; no public IPs; restrict inbound to app subnets via security groups.

Encryption at rest: KMS-managed keys for storage and backups where supported.

Encryption in transit: enforce TLS for client connections; restrict cipher suites per bank standard.

Backups and recovery: automated backups + defined retention; test restore regularly; define RPO/RTO targets.

High availability: multi-AZ / HA where supported; document failover behaviour.

Observability: metrics, logs (slow query, error logs), and alerts integrated with the bank monitoring stack.

Access control: separate admin vs app accounts; rotation of DB credentials; no shared admin accounts.

Patch management: define who patches and how (managed service windows or controlled manual patching).

Standard templates: parameter groups, option groups, subnet groups, security groups, tagging.

## 5.2 Reference baseline (proposed defaults)

| Control area | Proposed default | Notes to confirm |
| --- | --- | --- |
| Deployment model | Managed DB (RDS-style) in private subnets | Confirm service availability in HCS target region/version. |
| HA | Multi-AZ for production; single-AZ allowed for non-prod | Confirm supported HA modes per engine. |
| Backups | Daily automated backups + PITR where supported; retention 14–35 days | Confirm stakeholder baseline; storage cost implications. |
| Encryption at rest | Enabled using customer-managed or platform KMS keys | Confirm key ownership model and approval process. |
| Encryption in transit | TLS enforced; no plaintext allowed | Confirm app compatibility and certificate approach. |
| Monitoring | CPU, storage, IOPS, connections, replication lag, backup failures; alert thresholds defined | Align to bank monitoring tooling. |
| Logging | DB audit logs and slow query logs enabled; retention aligned to policy | Confirm log export method (OBS/LTS/etc.). |
| Credentials | Separate admin and app user; passwords rotated; no shared admin accounts | Integrate with secrets tooling later. |
| Network access | Only app subnets/SGs; restrict admin access via jump/bastion | Confirm bastion pattern in HCS. |
| Tagging | App, cost-centre, environment, owner, data-classification | Align to ABSA tagging standards. |

## 5.3 Terraform implementation approach for DB stacks

Implement DB infrastructure as a layered set of Terraform stacks/modules:

| Layer | What is provisioned |
| --- | --- |
| Layer 0 – Foundations | VPC/VNet equivalent, subnets, route tables, DNS, NTP, shared security groups, OBS bucket for state. |
| Layer 1 – Platform services | KMS keys, logging/audit sinks, monitoring integration, baseline IAM policies. |
| Layer 2 – Database baseline | Subnet group, security groups, parameter groups, option groups, backup configuration, RDS instance(s). |
| Layer 3 – App onboarding | Per-app DB/schema, per-app user, secrets placeholders, network rules for that app only. |

## 5.4 App onboarding for DBs (what app teams must provide)

To keep onboarding consistent, require a small set of inputs and generate standard outputs:

| Input from app team | Example | Why needed |
| --- | --- | --- |
| Environment | non-prod / prod | Selects the correct network, IAM, sizing, and approvals. |
| DB engine and version | PostgreSQL 14 (example) | Drives parameter groups and compatibility. |
| Sizing tier | small/medium/large (mapped to instance classes) | Controls cost and performance. |
| Connectivity | Source subnet/SG IDs that need DB access | Allows least-privilege inbound rules. |
| Data classification | Confidential / Restricted | Determines logging, encryption, and retention requirements. |
| Backup needs | Retention 14 days; RPO/RTO target | Sets backup retention and HA expectations. |
| Owner/contact | Team name, on-call distribution list | Operational routing and accountability. |

Standard outputs provided by the platform baseline:

RDS endpoint(s) and port (private).

Application DB username (password stored as secret, not emailed).

Security group rule references proving least-privilege access.

Backup/HA configuration summary (evidence for audit).

Links to runbooks (restore procedure, incident response, maintenance windows).

## 5.5 Example: MVP single VM deployment (confidence builder)

Before the DB baseline, run a controlled MVP that deploys a single VM (ECS/compute instance) into a non-production subnet. This proves: network reachability, IAM permissions, Terraform state backend, and Azure DevOps agent configuration.

MVP acceptance criteria:

Pipeline can run terraform init/plan/apply on the HCS agent without manual steps.

State is stored remotely (OBS) and can be re-used by a second engineer/pipeline run.

VM is created in the correct subnet with correct tags and security group rules.

A destroy pipeline can remove it cleanly (proves lifecycle control).

Evidence captured: work item link, PR link, pipeline run, plan artefact, approval record.

## 5.6 Example snippets (illustrative, not final)

Terraform provider configuration (illustrative):

provider "huaweicloud" {
  region         = var.region
  access_key     = var.access_key       # preferably injected as secret env var
  secret_key     = var.secret_key
  security_token = var.security_token   # only when using temporary creds
}

Terraform remote state in OBS via S3-compatible backend (illustrative):

terraform {
  backend "s3" {
    bucket                      = "tfstate-nonprod"
    key                         = "rds-baseline/terraform.tfstate"
    region                      = "<region>"                    # example only
    endpoint                    = "https://obs.<region>.<domain>"
    skip_credentials_validation = true
    skip_region_validation      = true
    skip_metadata_api_check     = true
    force_path_style            = true
  }
}

Azure DevOps YAML skeleton (illustrative):

stages:
- stage: Plan
  jobs:
  - job: terraform_plan
    pool: HCS-NonProd
    steps:
    - checkout: self
    - script: terraform fmt -check
    - script: terraform init -input=false
    - script: terraform plan -out=tfplan -input=false
    - publish: tfplan
      artifact: terraform-plan

- stage: Apply
  dependsOn: Plan
  condition: and(succeeded(), eq(variables['Build.SourceBranch'], 'refs/heads/main'))
  jobs:
  - deployment: terraform_apply
    environment: HCS-NonProd   # use approvals/checks on environment
    strategy:
      runOnce:
        deploy:
          pool: HCS-NonProd
          steps:
          - download: current
            artifact: terraform-plan
          - script: terraform apply -input=false tfplan

# 6. Work tracking, reporting, and personal organisation

Your priorities are: (1) developers always know what they are working on now and next, (2) simple reporting to stakeholders, and (3) personal organisation as platform lead (Verash Adams). This can be achieved inside Azure DevOps without introducing additional tools.

## 6.1 Minimum viable delivery operating model (no re-org required)

Use one Azure DevOps Project for the platform work (IaC + pipelines + standards).

Use Azure DevOps Boards for work items; do not rely on chat as the source of truth.

Create a small set of work item templates: 'Infra Change', 'Pipeline Change', 'Break/Fix', 'Architecture Decision', 'Meeting Action'.

Adopt a weekly iteration cadence with a simple 'Now / Next / Blocked' view.

Keep WIP limits: max 1–2 active items per engineer to avoid fragmentation.

## 6.2 Suggested work item structure

A simple hierarchy that works for both messy and mature landscapes:

Epic: e.g., 'HCS Landing Zone & DevOps Enablement'

Feature: e.g., 'MVP – Single VM via Terraform on self-hosted agent'

User Story: e.g., 'As a platform engineer, I can run terraform plan/apply from ADO using a pipeline identity'

Tasks: concrete steps (agent build, IAM setup, state backend, module creation, pipeline YAML, etc.)

Bugs: break/fix issues discovered during deployment

## 6.3 Weekly stakeholder report (copy/paste template)

Use this to send a short update (email/Teams message) each week:

Week ending: <date>
Progress (Done):
- <item 1>
- <item 2>

Now (In progress):
- <item 1>
- <item 2>

Next (Planned):
- <item 1>
- <item 2>

Risks / Blockers:
- <risk 1> (owner, ETA)

Decisions needed:
- <decision 1> (by when)

Evidence links:
- ADO board: <link>
- Key pipeline runs: <links>

## 6.4 Personal organisation as platform lead (Verash Adams) (practical)

Maintain a single 'Lead (Verash Adams)' swimlane: actions, decisions, and escalations you own.

Capture meeting actions as work items during the meeting (not after).

Use an 'Architecture Decisions' log: short ADRs (1 page) for key decisions (provider choice, state backend, IAM model, etc.).

Keep a 'Break/Fix' queue separate from planned work; review and prune weekly.

Block out 1–2 focus windows per week for design work; keep break/fix time-boxed.

# 7. Risk register (initial)

This is an initial risk register. Update likelihood/impact once Phase 0 answers and workshop outcomes are known.

| ID | Risk | Likelihood | Impact | Mitigation / control | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Azure DevOps Services unreachable from HCS agent due to restricted internet egress (or proxy not configured). | Medium | High | Confirm ADO type (Services vs Server). If Services, request network allow-list + proxy; otherwise deploy ADO Server internal. | <You/Network> | Open |
| R2 | Terraform provider mismatch with HCS version/features; provider becomes unmaintained or missing key resources. | Medium | High | Validate supported provider for the target HCS version in workshop. Prefer actively maintained provider. Pin versions and test in non-prod. | <You/Huawei> | Open |
| R3 | Use of long-lived AK/SK in pipelines increases credential exposure risk. | High (if used) | High | Use agency + temporary credentials if possible. If forced to use AK/SK, implement rotation, least privilege policies, secret storage controls, and audit. | <You/Sec> | Open |
| R4 | No clear separation of duties for production applies (single approver). | Medium | High | Establish environment approvals in ADO; require 2nd approver for prod; protect main branch; keep audit evidence. | Verash Adams | Open |
| R5 | Terraform remote state backend (OBS) not properly secured or lacks locking, causing state corruption. | Medium | High | Design state bucket per env; restrict access; enable versioning; implement process controls (single apply at a time) or tooling to lock. | <You> | Open |
| R6 | DB baseline does not meet stakeholder expectations (backup retention, HA, logging, encryption). | Medium | High | Obtain ABSA baseline reference if possible. Run workshop to confirm requirements; document deviations and approvals. | <You/DBA> | Open |
| R7 | Operational ownership unclear for managed DBs (patch windows, monitoring, incident response). | Medium | Medium | Define RACI: platform vs DBA vs app team. Create runbooks and alert routing. Agree on maintenance windows. | <You/Ops> | Open |
| R8 | Messy landscape causes uncontrolled changes outside Terraform (drift). | High | Medium | Implement drift detection plans; restrict console access; adopt 'Terraform is the source of truth' policy for managed resources. | <You> | Open |
| R9 | DB network exposure (wrong security group rules / accidental public access). | Low | High | Default DB subnets to private only; deny public IPs; require SG rules to reference known app SGs; run security reviews. | <You/Sec/Net> | Open |
| R10 | Backup/restore not tested; false confidence in recovery. | Medium | High | Schedule quarterly restore tests in non-prod; capture evidence; define and monitor backup failure alerts. | <DBA/Ops> | Open |

# 8. Huawei engagement: meeting with Jenile and workshop plan

## 8.1 Summary of meeting with Jenile (Huawei) – draft notes

This section captures the key points to communicate back to Pragasen. Update with the exact date/time and action owners.

Objective: align on the technical enablement required to deploy into Huawei Cloud Stack using Terraform and Azure DevOps self-hosted agents.

Outcome: agreed to run targeted workshops to confirm provider support, IAM patterns (agency vs AK/SK), RDS service capabilities, and network prerequisites.

Key ask from Huawei: provide HCS API endpoints, tenant/region details, and supported Terraform provider guidance for the specific HCS version.

Key ask from us: confirm whether temporary credentials via agency are enabled/approved for pipelines; confirm any enterprise constraints (proxy, certificates, outbound rules).

## 8.2 Proposed workshop backlog (recommended)

| Workshop | Objectives | Outputs | Attendees (suggested) |
| --- | --- | --- | --- |
| W1 – Identity & IAM for automation | Decide pipeline identity model; agency/role design; least privilege policies. | Agreed IAM pattern + policy templates + credential issuance flow. | You, Security/IAM, Huawei IAM SME, RedMps infrastructure engineers |
| W2 – Terraform provider & state backend | Confirm provider choice, versions, endpoints, remote state in OBS. | Provider decision record + working terraform init/plan on agent. | You, Huawei Terraform SME, RedMps infrastructure engineers |
| W3 – Networking for pipelines and DBs | Connectivity from agent to ADO and HCS APIs; DB subnet/security design; DNS/NTP/proxy. | Network diagram + firewall rules + confirmed subnets/SG patterns. | You, Network team, Huawei network SME |
| W4 – RDS baseline capability review | Confirm supported engines, HA, backup features, encryption/logging options. | RDS baseline requirements matrix + gaps/decisions list. | You, DBAs, Huawei RDS SME, Security |

# 9. Immediate next steps (2-week practical plan)

Assuming we want to build confidence quickly, the following plan is realistic and structured:

| Step | Outcome | Dependencies |
| --- | --- | --- |
| 1) Confirm Phase 0 decisions | Provider choice, ADO type, credential model, approver model, baseline references | Pragasen + Huawei + Security |
| 2) Build self-hosted agent VM (non-prod) | Agent online in ADO Agent Pool with required tools installed | Compute provisioning + network |
| 3) Establish Terraform remote state (OBS) | State bucket created, secured, versioned; tested with terraform init | OBS + IAM permissions |
| 4) Create pipeline identity + policies | Non-prod IAM user/agency with least privilege for VM creation | IAM team / Huawei guidance |
| 5) MVP pipeline: deploy single VM | End-to-end proven: plan/apply/destroy with evidence | All above |
| 6) Baseline RDS workshop + design | Agreed DB baseline requirements; Terraform module plan | DBA + Security + Huawei |

# Appendix A – References (URLs)

External references used for this draft (confirm applicability to your HCS version and enterprise policy):

Microsoft Learn – Azure Pipelines agents: https://learn.microsoft.com/en-us/azure/devops/pipelines/agents/agents?view=azure-devops

Microsoft Learn – Deploy a self-hosted Linux agent: https://learn.microsoft.com/en-us/azure/devops/pipelines/agents/linux-agent?view=azure-devops

Terraform Registry – HuaweiCloud providers namespace: https://registry.terraform.io/namespaces/huaweicloud

Terraform Registry – HCSO provider guide for remote state backend (OBS/S3): https://registry.terraform.io/providers/huaweicloud/hcso/latest/docs/guides/remote-state-backend

Huawei Cloud IAM API – temporary access keys and security tokens (agency): https://support.huaweicloud.com/intl/en-us/api-iam/iam_04_0101.html

Huawei Cloud Stack / Huawei documentation – OBS provides S3-compliant REST API (confirm your version): https://support.huawei.com/enterprise/en/doc/EDOC1100453116/c514699a/clients-and-services